## C1 and C2
Appendix C1
Bilding Corporation
Network Analysis for Livingstone School Construction Project (in weeks)
Normal Methods
| Key: | Activity | [16 empty] | 35
79
|  | Critical Path Activity | [13 empty] | O
5
Dummy Activity (Dependency)
30
|  | Earliest Start Time | [8 empty] | 31 |  |  |  | 59
|  | Latest Finish Time | [7 empty] | E |  |  |  | I | 59 | K
| Start | [8 empty] | 4 |  |  |  | 8 |  | 10 |  |  |  |  | Finish
| 0 | A | 3 | B | 11 | C | 23 | D | 26 | F | 31 | G | 51 |  | H |  | 69 | M | 74 | N | 79
| 0 | 3 | 3 | 8 | 11 | 12 | 23 | 3 | 26 | 5 | 31 | 20 | 51 |  | 12 |  | 69 | 5 | 74 | 5 | 79
[14 empty] | J |  | L
[5 empty] | Original | CLIPS | Revised | [6 empty] | 10 | 61 | 5
[5 empty] | Cost | Saving | Cost | [7 empty] | 64
| Costs: | Activity |  |  | £'000 | % | £'000 | Page
|  | A | Newt relocation |  | 15 |  | 15 | 11
|  | B | Archaeological dig |  | 35 |  | 35 | 19 | [8 empty] | P
|  | C | Land decontamination |  | 100 |  | 100 | 22 | Conclusion: | [5 empty] | Page |  | 30 |  | 56
|  | D | Ground preparation |  | 50 | 10 | 45 | 4,9 | Although the cost of the project remains within the permitted | [9 empty] | 79
|  | E | Services |  | 65 |  | 65 | 9 | capital allocation (£2.5m), the project requires a total of 79 weeks. | [5 empty] | 22,30
|  | F | Foundations |  | 120 | 20 | 96 | 4,9 | For timely completion the project must be completed in 72 weeks. | [5 empty] | 22,28
|  | G | Main structure |  | 790 | 10 | 711 | 4,9 | This implies that the building will not be ready as required by
|  | H | Ancillary structures |  | 410 | 10 | 369 | 4,9 | mid-July, and indeed will not be available until September.
|  | I | Plumbing |  | 85 |  | 85 | 9 | This would involve a delay in the opening of the school,
|  | J | Electrical |  | 105 |  | 105 | 9 | which is not acceptable to users. | [5 empty] | 22
|  | K | Heating |  | 70 |  | 70 | 9
|  | L | Plastering |  | 45 |  | 45 | 9
|  | M | Decoration |  | 50 |  | 50 | 9
|  | N | Fitting out/Snagging |  | 110 | 10 | 99 | 4,9
|  | O | Car park |  | 70 |  | 70 | 9
|  | P | Playing field |  | 60 |  | 60 | 9
2020
|  | Add: | Professional Fees (10%) of D to P |  |  |  | 187 | 23
2207
|  | Add: | Property Projects Fee (2.5%) |  |  |  | 55.175 | 22
|  | Add: | Contingencies |  |  |  | 220.7 | 23
|  |  | Total Projected Cost |  |  |  | 2482.875
Appendix C2
Bilding Corporation
Network Analysis for Livingstone School Construction Project (in weeks)
Accelerated (Crash) Methods
| Key: | Activity | [16 empty] | 34
72
|  | Critical Path Activity | [13 empty] | O
5
Dummy Activity (Dependency)
29
|  | Earliest Start Time | [8 empty] | 29 |  |  |  | 55
|  | Latest Finish Time | [7 empty] | E |  |  |  | I | 55 | K
| Start | [8 empty] | 3 |  |  |  | 6 |  | 8 |  |  |  |  | Finish
| 0 | A | 3 | B | 11 | C | 23 | D | 26 | F | 29 | G | 49 |  | H |  | 63 | M | 67 | N | 72
| 0 | 3 | 3 | 8 | 11 | 12 | 23 | 3 | 26 | 3 | 29 | 20 | 49 |  | 12 |  | 63 | 4 | 67 | 5 | 72
[14 empty] | J |  | L
[14 empty] | 10 | 59 | 4
59
Costs:
P
[5 empty] | Normal | Crash | Normal | Crash | Cost | Time | Cost per | Projected |  |  |  |  | 30 |  | 56
[5 empty] | Cost | Cost | Duration | Duration | Increase | Saving | Week | Cost | [6 empty] | 72
|  | Activity |  |  | £'000 | £'000 | (Weeks) | (Weeks) | £'000 | (Weeks) | £'000 | £'000 | Page
|  | A | Newt relocation |  | 15 | 14.55 | 3 | 3 |  |  |  | 15 | 11
|  | B | Archaeological dig |  | 35 | 35 | 8 | 8 |  |  |  | 35 | 19 | The cheapest way to save 1 week is to crash activity M.
|  | C | Land decontamination |  | 100 | 100 | 12 | 12 |  |  |  | 100 | 22 | Activities O and P are not on the critical path and no advantage accrues from
|  | D | Ground preparation |  | 45 | 45 | 3 | 3 |  |  |  | 45 | 27,App C1 | crashing these activities. This also applies to activity H.
|  | E | Services |  | 65 | 75 | 4 | 3 | 10 | 1 | 10 | 75 | 9,27 | Activity K is still on the critical path and is the next most attractive option.
|  | F | Foundations |  | 96 | 112 | 5 | 3 | 16 | 2 | 8 | 112 | 27,App C1 | Activity F appears to be the next cheapest way to save time, but if activity F
|  | G | Main structure |  | 711 | 781 | 20 | 17 | 70 | 3 | 23.3333 | 711 | 27,App C1 | reduces to 3 weeks, activity E lies on the critical path instead of activity F.
|  | H | Ancillary structures |  | 369 | 387 | 12 | 10 | 18 | 2 | 9 | 369 | 27,App C1 | Extra expenditure of £16K therefore only produces a saving of 1 week.
|  | I | Plumbing |  | 85 | 105 | 8 | 6 | 20 | 2 | 10 | 105 | 9,27 | Also crashing activity E costs £26K in total for a saving of 2 weeks, costing
|  | J | Electrical |  | 105 | 118 | 10 | 9 | 13 | 1 | 13 | 105 | 9,27 | £13K per week saved in total.
|  | K | Heating |  | 70 | 84 | 10 | 8 | 14 | 2 | 7 | 84 | 9,27 | Crashing activity I looks the next cheapest, but only 1 week would be saved
|  | L | Plastering |  | 45 | 56 | 5 | 4 | 11 | 1 | 11 | 56 | 9,27 | for extra cost of £20K, as the critical path would pass along activities J and L.
|  | M | Decoration |  | 50 | 56 | 5 | 4 | 6 | 1 | 6 | 56 | 9,27 | Also crashing activity L results in a 2 week saving at a total cost of £31K.
|  | N | Fitting out/Snagging |  | 99 | 119 | 5 | 4 | 20 | 1 | 20 | 99 | 27,App C1 | Saving time by crashing activities G or N is more expensive, and therefore the
|  | O | Car park |  | 70 | 75 | 5 | 4 | 5 | 1 | 5 | 70 | 9,27 | required further saving of 4 weeks come by crashing activities E, F, I and L.
|  | P | Playing field |  | 60 | 72 | 30 | 26 | 12 | 4 | 3 | 60 | 9,27
[12 empty] | 2097 |  | Conclusion: | [5 empty] | Page
[8 empty] | Add: | Professional Fees (10%) of D-P |  |  | 194.7 | 23 | The project cost exceeds the capital budget of £2.5 million by | [5 empty] | 22,30
[12 empty] | 2291.7 |  | £78,000 if the projected is expedited to an expected completion
[8 empty] | Add: | Property Projects Fee (2.5%) |  |  | 57.2925 | 22 | time of 72 weeks. The project completion remains highly risky | [5 empty] | 22,28
[8 empty] | Add: | Contingencies |  |  | 229.17 | 23 | as most activities now lie on the critical path, so a delay to any
[9 empty] | Total Projected Cost |  |  | 2578.1625 |  | one of these activities will delay the whole project.

## C3 and C4
Appendix C3(1)
Project Management
Key Elements |  |  | Weaknesses on Dampcorse/Livingstone Projects |  |  | Page | Proposal | Responsibility
Establish Objectives
| Define strategic aims of project |  | Crude adaptation of previous design |  |  | 13 | Consult with users | Education Directorate
| Establish constraints |  | Inadequate budget for project |  |  | 14,22,30
| Define acceptable timescales |  | Committed to impossible timescale |  |  | 13,14 | Feasibility confirmed | C. Ling
Identify customer needs
| Consultation with users |  | No consultation |  |  | 13 | Constitute Board of | Education Directorate
| Present choices to user representatives |  | No board of governors at planning stage |  |  | 13 | Governors within 6 weeks
| Negotiate level of user expectations |  | Community expectations unrealistic |  |  | 13 | and consult over design
| Define priorities |  | Most outcomes scaled back not prioritised |  |  | 13,14 | and priorities within £2.5
| Comprehensive needs definition documented |  | Not done |  |  | 14 | million budget.
| Secure user acceptance |  | Not done |  |  | 13
Define acceptable solution
| Define suitable solution to meet outcomes |  | Inappropriate design adopted |  |  | 13,14 | Agree suitable design | Education Directorate
| Confirm feasibility in terms of constraints |  | Over-optimistic proposals presented |  |  | 14 | Feasibility confirmed | C. Ling
| Confirm acceptability |  | No independent appraisal of feasibility |  |  | 14 | Feasibility confirmed | C. Ling
Establish project team
| Secure user commitment |  | No consultation: top-down opinion |  |  | 13,14 | Governor representation | Education Directorate
| Secure funding and approval from funders |  | Budget inadequate |  |  | 14,22,30 | Minor shortfall to fund | Education Directorate
| Agree roles and responsibilities |  | Ill-defined and based on assumed roles |  |  | 14 | Formal project team | Property Projects
| Set up reporting framework |  | Largely verbal and unofficial |  |  | 14 | Formal written reports
[7 empty] | and minutes | Property Projects
Plan activities
| Define all required tasks and draw up tender specifications |  | Some key tasks omitted |  |  | 13,14 | Checklists to confirm completion | Property Projects
| Identify required resources and seek tenders | [5 empty] | Already done
| Acquire required resources and select contractors |  | Inadequate screening of capabilities and stability |  |  | 14 | Confirm financial status of contractors | Finance
| Build in contingencies and failsafe strategies |  | Contingency plans and resources inadequate |  |  | 14 | Documentation of alternatives | Property Projects
Appendix C3(2)
Project Management
Key Elements (continued) |  |  | Weaknesses on Dampcorse/Livingstone Projects
Scheduling
| Establish dependencies within identified constraints |  | Not formally established in written plan |  |  | 13,14 | Already done
| Identify consecutive tasks |  | Failure to apply critical path analysis |  |  | 14 | Already done
| Identify tasks which can be performed concurrently | [5 empty] | Already done
| Overcome anticipated delays and bottlenecks |  | Not clearly defined in advance |  |  | 14 | Already done
Control
| Regular collection of data on progress |  | Haphazard and compromised by staff absence |  |  | 14 | Regularised procedures | Property Projects
| Timely reporting of progress and quality to responsible officials |  | Little formal reporting |  |  | 14 | Regular written reporting cycle | Property Projects
| Respond to delays or non-performance |  | Problems compounded by tardy reaction |  |  | 13,14 | Identify responsibilities with deadlines | Property Projects
| Hold managers accountable for achieving planned performance |  | Confusion, culture of blame, inconsistent |  |  |  | Clear roles and responsibilities defined | Property Projects
|  |  | micromanagement by senior Education staff |  |  | 13,22
| Initiate corrective action and authorise variations |  | Excessive variations due to changes to user |  |  |  | All queries and suggestions routed via | Education Directorate
|  |  | requirements, not properly authorised or agreed |  |  | 13 | project team
| Enforce penalty clauses on contractors |  | No evidence of contractors being held |  |  |  | Incorporate CLIPS Board best | Property Projects
|  |  | responsible for delays or even if clauses exist |  |  | 13,14 | practice into contract terms
| Deploy contingent resources as required |  | Inefficiently deployed |  |  | 14 | Prior contingency planning | Property Projects
Inspection
| Quality control on activities |  | Little undertaken due to false economy |  |  | 13,14 | Document requirements | Property Projects
| Inspection and review |  | Not performed |  |  | 13 | Checklist to confirm completion | Property Projects
| Create schedule of defects |  | Not performed |  |  | 13 | Undertake to plan | Property Projects
| Agree on corrective action |  | Not performed |  |  | 13 | Undertake to plan | Property Projects
| Inspection and clearance of defects |  | Not performed |  |  | 13 | Undertake to plan | Property Projects
| Release retentions |  | Contractor allowed to evade responsibilities |  |  | 13 | Undertake to plan | Property Projects
Implementation
| Undertake commissioning activities |  | Not performed |  |  | 13 | Undertake to plan | Property Projects
| Training and user familiarisation |  | Not performed |  |  | 13 | Undertake to plan | Property Projects
| Incorporate further required resources |  | Not identified |  |  | 13,30 | Identify enhancements | Education Directorate
Post-implementation review
| Establish level of user satisfaction |  | Not performed |  |  | 13,30 | Undertake to plan | Property Projects
| Review performance |  | Not established |  |  | 13,14 | Undertake to plan | Education Directorate
| Define further requirements |  | Not done |  |  | 14,30 | Undertake to plan | Education Directorate
| Incorporate learning into future project plans |  | No evidence of this |  |  | 22,30 | Undertake to plan | Education Directorate
Project Management
| Key Elements | Weaknesses on Dampcorse Project |  | Proposal | Responsibility
Element 1
| Step1 | Weakness 1 |  | Proposal 1 | A.N. Other
|  | Weakness 2 |  | Proposal 2 | A.N. Other
|  |  |  | Proposal 3 | A.N. Other
| Step2 | Weakness 3 |  | Proposal 4 | A.N. Other